## Summary
Unit Testcase Execution Report
Project Name:
Revision History
Sl. No	Version	Created On	Description	Created By	Reviewed By	Approved By
1	0.1	3 Feb 17	Initial Draft	M. Mangala Jothi

Note:	Versions increment by 0.1 for every revision

## Unit_Testing
Project Version:	Alchemy	Testing Round #:	Unit Testing without integration to BPM.
Module/Functionality:	About Prospect UI	Sprint #:
Test Case Doc #:	v0.1	Developer / Tester:	Dinesh Subramaniyam / Arunkumar
Repository URL:
TEST CASES					EXECUTION REPORT
Test Case #	Description	Execution Steps	Expected Output	Additional Remarks	Browser	Actual Output	Result Nature	Severity	Status	Closed By	Closed On	Revision#
A001	Check input type and max character length.	Step 1: First Name, alphabets & space, max 40.	Input using specified type should be possible till max length is reached.		Firefox	Result as expected.
		Step 2: Middle Name, alphabets & space, max 40.				Result as expected.
		Step 3: Last Name, alphabets & space, max 40.				Result as expected.
		Step 4: Mobile number, only numbers. (12 chars including 91).				Result as expected.
		Step 5: If Minor is yes, Guardian name, alphabets & space, max 120.				Result as expected.
		Step 6: Check EmailId (5-120), as per industry Validations.				Result as expected.
		Step 7: Check Alternate-EmailId (5-120), as per industry Validations.				Result as expected.
		Step 8: Mothers Maiden name, alphabets & space, max 120.				Result as expected.
		Step 9: Father name, alphabets & space, max 120.				Result as expected.
		Step 10: Spouse name, alphabets & space, max 120.				Result as expected.
		Step 11: Staff Number, numeric, max 12.				Result as expected.
		Step 12: Nationality, alphabets & space, max 15.				Result as expected. However, this value needs to be validated with Country of Birth. Check with a session variable.
A002	Check default values.	Step 1: Check Mobile number field.	91 should be defaulted in the screen.			Result as expected.
		Step 2: Check Prefered Communication	English			Result as expected.
		Step 3: Check Country field.	INDIA			Result as expected.
		Step 4: Check Politically Exposed Person	No			Result as expected.
A003	Check drop down boxes.	Step 1: Check Title, Guardian Relationship with Minor, Gender, Maritial Status, Preferred language for Communication, Gross Annual Income, Occupation, Politically Exposed Person [PEP].	Values in drop downs should be as given in Common List of Value Master.xlsx. / Only one value from the drop down should be selectable.			Confirm the LoVs are coming from JSON structure. / Title - Result as expected. Confirm the LoVs are coming from JSON structure. / Guardian Relationship with Minor - is not presented as a drop down. / Martial Status - Even when not coming from LoVs for testing purpose, ensure LoVs from masters are copied and hardcoded to avoid spelling mistake. / Preferred Language - Populate more values to select.
A004	Check field dependency.	Step 1: Select various DOBs that will make the Prospect a Minor or a Senior Citizen or not both.	By selecting DOB - Age should be derived. Based on age the Prospect should be identified as Senior Citizen, Minor age or not. / Select DOB to create a "minor". Guardian's Relationship with Minor and Guardian Relationship Email should be enabled for input.			1. Minor and Senior Citizen identified correctly. / 2. If Minor, Guardian Name, Relationship are enabled for entry / selection.
		Step 2: Keep Father's Name blank, Spouse Name cannot be blank.				Submit / save happens even when both Father's name and Spouse name are left blank.
		Step 3: Keep Spouse Name blank, Father's Name cannot be blank.				Submit / save happens even when both Father's name and Spouse name are left blank.
		Step 4: If Form 60/61/49 is selected, Father's Name is mandatory.				The code needs to check if Identity Info is Form 60/61/49. If so, Father's name should be mandatory. Unable to test now. Suggest introduce a session variable and check if the condition works.
A005	DB field.	Step 1: Check that no field that has Alchemy in "Hidden in" is not on the screen.				Result as expected.
A006	Save / submit.	Step 1: Save the values level with only mandatory fields fields filled.	Save should take place.			Result as expected.
		Step 2: Save the values with all fields except Optional fields filled.	Save should take place.			Result as expected.
		Step 3: Save the values with all fields filled.	Save should take place.			Result as expected.
		Step 4: Save the values with each mandatory field not filled.	Save should not take place. Error display as per UI specifications.			Able to Submit / save without filling Occupation, Gross Annual Income, Language, PEP filled.
A007	Next	Step 2: Will switch to the next Data Groups.	Next should take place.			Result as expected.
	Previous	Step 2: With switch to the Previous Data Groups	previous should take place.			Result as expected.
A008	Perform UI checks.	As per Sastra UI Review Checklist.				1. Mandatory and conditional mandatory fields - colour of * should be different. It is the same now. / 2. Submit / save without filling mandatory field(s) - mandatory field input box should have border in RED colour. Default CSS alert should be displayed. / 3. No. of characters left to fill to be displayed in all text box fields. / 4. Change Maritial Status to Marital Status. / 5. Change Father Name to Father's Name. / 6. Change Politically Exposurse to Politically Exposed. / 7. Gender selections - font used sees big compared to data entry font (Arial 14). / Do spell check.

## Sheet2
Low	New
Medium	Clarified
High	Rejected
Critical	Rectified
Show Stopper	Closed
	Deferred